## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | Captain Morgan
Group Member: | Michael Moon |  | Progress Classes: | Ahead
Group Member: | Alexander Cowan |  |  | On-track
Group Member: | Michael Whyte |  |  | Behind
Group Member: | Morgan Cassar |  |  | Way Behind
Tutor: | Seyedali Mirjalili | Anna Bazzano
Class: | Advanced Programming techniques
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Michael Moon | Alexander Cowan | Michael Whyte | Morgan Cassar
|  |  | Group Formed |  | Weekly Contribution | Ahead | Ahead | Ahead | Ahead
|  |  | MS Team created |  | Issues | Ahead | Ahead | Ahead | Ahead
|  |  | Git Repo created |  | Other Notes | Ahead | Ahead | Ahead | Ahead
|  | Progress | Ahead
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Michael Moon | Alexander Cowan | Michael Whyte | Morgan Cassar
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | On-track
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues |  | On-track
|  |  | Main menu |  | Other Notes |  |  | On-track
|  |  | User Prompt (for gameplay), but no/minimal error checking |  |  | On-track
|  |  | Linked List implementation | [5 empty] | On-track
|  |  | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required | [5 empty] | On-track
|  |  | ADT implementation for storing information, game loop logic not required |  |  |  | On-track
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Michael Moon | Alexander Cowan | Michael Whyte | Morgan Cassar
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | On-track | On-track | On-track | On-track
|  |  | Initialisation of data strctures for new game |  | Issues | On-track | On-track | On-track | On-track
|  |  | Write Tests Cases for common uses |  | Other Notes | On-track | On-track | On-track | On-track
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic |  |  | On-track | On-track | On-track | On-track
|  | Progress | On-track
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Michael Moon | Alexander Cowan | Michael Whyte | Morgan Cassar
|  |  | Fully complete implementation and error free |  | Weekly Contribution | On-track | On-track | On-track | On-track
|  |  | Full error checking of user prompt |  | Issues | On-track | On-track | On-track | On-track
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes | On-track | On-track | On-track | On-track
|  |  | Final Tests |  |  | On-track | On-track | On-track | On-track
|  |  | Group Report Written |  |  | On-track | On-track | On-track | On-track
|  | Progress | On-track